## POA&M
Meridian Pay - Plan of Action and Milestones (POA&M)
The master list of known weaknesses and how they get fixed. This is the working heart of a security programme.
ID | Weakness | Source | Severity | Affected system | Planned remediation | Owner | Target date | Status
P-001 | Audit logs not reviewed on a schedule (AU-6) | CSF self-assessment | Moderate | Admin Console (S7) | Define weekly log-review process and assign it | Security team |  | Open
P-002 | Backup restores not tested regularly (CP-10) | CSF self-assessment | Moderate | Core Banking (S3) | Add quarterly restore test to the calendar | Platform team |  | Open
P-003 | No formal patch SLA (SI-2) | Risk assessment | Moderate | All systems | Set and document patch timelines by severity | Platform team |  | In progress
P-004 | Quarterly access review not yet formal (AC-2) | CSF self-assessment | Low | All systems | Stand up quarterly access review with owners | Platform team |  | Open
P-005 | Supplier risk assessments incomplete (GV.SC) | CSF self-assessment | High | Third parties | Assess CardaX, VerifyNow, messaging provider | Head of Risk |  | Open